## Dashboard
IoT Embedded Water Filtration System — Project Tracker
Project Lead | Nash | Final Defense | October 10, 2026
Team | Nash • Alejandro • Edgar | Feature Freeze | October 8, 2026
Current Phase | Phase 2 — Backend API core implemented in TypeScript (auth, telemetry, alerts, test runs, calibration, lab validation, maintenance, settings, devices, users); telemetry ingestion, CSV export, and alert-generation logic remain. Frontend v1 complete; Phase 0 hardware gaps pending.
TASK METRICS
Total Tasks |  | Done |  | In Progress | Waiting Client
Overall Progress
KEY MILESTONES | Target | Status | Exit Criteria
Phase 0 Closeout | Sep 15 | Waiting Client | Repo + frontend foundation committed locally on feature/frontend-foundation; DB/API/simulator pending
Foundation + Simulator | Sep 18 | In Progress | 8-screen frontend committed locally; connect simulator/API data pipeline, then push/merge through normal branch workflow
Web MVP | Sep 23 | In Progress | 8-screen frontend complete; connect simulator/API data pipeline
ESP32 Data Integration | Sep 30 | Not Started | Real sensor data reaches dashboard
Hardware + Software Integration | Oct 3 | Not Started | Hardware + software end-to-end
Full Integration | Oct 7 | Not Started | Calibration, reliability, exports verified
Feature Freeze | Oct 8 | Not Started | Bug fixes only
Final Defense | Oct 10 | Not Started | Stable demo + backup plan
CURRENT BLOCKERS
• Exact turbidity sensor model missing
• Pump/UV-C electrical specs missing
• Final verified pin map not yet confirmed
• Approved water-quality thresholds missing
• Need pump/UV-C control vs monitor-only decision
• Need final sampling/save/cycle timing rule
• Backend API implemented (Express + TypeScript, commit 598f0e1) per API ROUTES PLAN — needs team review/approval; telemetry ingestion + CSV export + alert-generation logic still outstanding.

## Project Tracker
Task ID | Phase | Workstream | Task | Owner | Priority | Status | Target | What Needs To Be Done | Dependencies / Inputs
P0-01 | Phase 0 | Requirements | Receive completed Phase 0 requirements form | Nash | High | Done | Sep 11 | Archive client answers and use them as development basis. | Client response
P0-02 | Phase 0 | Requirements | Review client answers and identify gaps | Nash | High | Done | Sep 14 | Separate confirmed requirements from blockers and pending hardware details. | P0-01
P0-03 | Phase 0 | Hardware Inputs | Confirm turbidity sensor exact model/link | Edgar | High | Waiting Client | Sep 15 | Get exact model, voltage/output type and datasheet. | Client hardware team
P0-04 | Phase 0 | Hardware Inputs | Confirm pump, UV-C, relay and power specifications | Edgar | High | Waiting Client | Sep 15 | Collect model, voltage, current, relay type and power supply details. | Client hardware team
P0-05 | Phase 0 | Control Rules | Confirm whether pump and UV-C are controlled or only monitored | Nash | Critical | Waiting Client | Sep 15 | Get explicit yes/no control matrix for pump and UV-C. | Client/adviser decision
P0-06 | Phase 0 | Thresholds | Obtain approved alert thresholds | Nash | High | Waiting Client |  | Obtain adviser/research-team approved numerical pH, turbidity, TDS, temperature and flow alert thresholds. Frontend keeps them unconfigured until approved. | Research adviser/lab criteria
P0-07 | Phase 0 | Data Policy | Finalize sampling, save interval and cycle rule | Nash | High | Waiting Client | Sep 16 | Separate sensor sample rate, database save rate, 1-L target and 1-hour maximum. | Client/adviser clarification
P1-01 | Phase 1 | Repository | Create GitHub repository and folder structure | Nash | High | Done | Sep 15 | Create frontend, backend, firmware, database, simulator and docs folders; add README, .gitignore and .env.example. | Tech stack frozen
P1-02 | Phase 1 | Architecture | Write architecture and API contract v1 | Nash | High | In Progress |  | Architecture documentation is drafted. Finalize domain endpoint paths, request/response payloads, error format, pagination/filter conventions and shared telemetry contract. | P0-05, P0-07
P1-03 | Phase 1 | Dev Environment | Set up local development environments | Nash | High | Done | Sep 16 | Install Node, VS Code, Git, PlatformIO; define branch and formatting rules. | P1-01
P1-04 | Phase 1 | Database | Create Supabase project and environment config | Alejandro | High | Done | Sep 16 | Create project, secure keys, .env setup and access rules. Local Supabase dev stack running via Docker (npx supabase start / db reset); backend/.env + .env.example configured with service-role/anon keys. Hosted/production Supabase project still pending — see P8-01. Commit f4b9ce9 on feature/backend-init. | P1-01
P1-05 | Phase 1 | Simulator | Create simulated pre/post sensor generator | Alejandro | High | In Progress | Sep 18 | Generate fake pre/post pH, turbidity, TDS, temperature, flow and status payloads. backend/scripts/seedTestData.ts generates 5 simulated pre/post reading cycles per test run directly into sensor_readings (pH, turbidity, TDS, temperature, flow rate) for local testing — see docs/API_REFERENCE.md. This seeds the DB directly rather than acting as a live device posting over HTTP; a continuous HTTP-based simulator still depends on the ingestion endpoint in P2-02. Commit 598f0e1 on feature/backend-init. | P1-02
P2-01 | Phase 2 | Database | Design and create core database schema | Alejandro | Critical | Done | Sep 18 | Create users, devices, telemetry, test_runs, alerts, calibrations, lab_tests and maintenance tables. Implemented via two migrations: devices, sensors, sensor_readings, test_runs, alerts (+alert_state_changes), calibration_records, laboratory_validation_records, profiles (f4b9ce9), plus maintenance_records, maintenance_reminders, app_settings, thresholds, notification_providers, data_retention_policy (598f0e1). Business-rule fields (taxonomies, thresholds) kept free-text/jsonb pending P0-06/P0-07 — see backend/docs/SCHEMA_TBD_LOG.md. | P1-04, P1-02
P2-02 | Phase 2 | Backend API | Build telemetry ingestion endpoint | Alejandro | Critical | Done | Sep 19 | Validate device ID, payload types, timestamps and missing fields; save telemetry. Implemented: POST /devices/:id/readings — batched ingestion, validates each reading's category/position/value against the device's registered sensors rows, skips (not fails) invalid/unregistered entries individually, and bumps devices.last_seen_at/connection_state as a heartbeat. Authenticated via a placeholder X-Device-Key shared secret, not the real device-auth decision (PENDING_DECISIONS §8). See docs/API_REFERENCE.md → Devices. Implemented on feature/backend-init (uncommitted as of this tracker update). | P2-01
P2-03 | Phase 2 | Backend API | Build latest-status and history endpoints | Alejandro | High | Done | Sep 20 | Add latest reading, date filters, history and pagination. Implemented: GET /telemetry (filters: from/to/testRunId/deviceId/parameter/stage, pagination), GET /telemetry/current (latest per sensor), GET /telemetry/chart, GET /telemetry/:id, plus GET /telemetry/stream (SSE) and GET /dashboard/summary. See docs/API_REFERENCE.md. Commit 598f0e1 on feature/backend-init. | P2-01
P2-04 | Phase 2 | Auth | Implement user authentication and roles | Alejandro | Medium | In Progress | Sep 23 | Configure Supabase Auth and backend role checks. Supabase Auth wired end-to-end: POST /auth/login¦logout¦refresh¦password-reset, GET /auth/me, PATCH /users/:id/role. profiles.role auto-provisioned via a DB trigger. Role-based authorization checks are NOT enforced yet — every authenticated user can call every route — pending a roles/permissions decision (docs/PENDING_DECISIONS.md §9). Commit 598f0e1. | P2-01
P2-05 | Phase 2 | Alerts | Implement alert/event storage logic | Alejandro | High | In Progress | Sep 24 | Support sensor, offline, no-flow, pump, UV-C, filter and water-quality alert categories. Storage/API implemented: alerts table (+source/title/message), GET /alerts, GET /alerts/:id, PATCH acknowledge/resolve, GET /alerts/stream (SSE), alert_state_changes audit trail. No automatic alert-GENERATION logic yet — nothing evaluates sensor readings/device faults into alert rows — blocked on P0-06 thresholds and P0-05 control-authority decisions. Commit 598f0e1. | P0-06, P2-01
P2-06 | Phase 2 | Exports | Implement CSV export | Alejandro | Medium | Not Started | Sep 25 | Export telemetry, test runs and comparison data with date filters. Not started. Candidate endpoint: GET /export/csv per docs/API_ROUTES_DRAFT.md §8; column set/order still TBD (PENDING_DECISIONS §12). Tracked in docs/tracker/todo.md. | P2-03
P3-01 | Phase 3 | Frontend | Create React + TypeScript + Vite frontend | Nash | Critical | Done | Sep 16 | React + TypeScript + Vite + Tailwind frontend completed with routing, responsive shell, typed service boundaries, mock adapters, CSV export and backend-integration-ready API client. Committed locally as 0a28ed012707b57c9dc10d5ce908bf8b0621aa54 — feat(frontend): build integration-ready application UI. Commit includes 79 approved files across frontend/, docs/ui/, README.md and docs/DEVELOPMENT.md; frontend/.gitkeep removed. Audit clean; no secrets or prohibited files. | P1-01
P3-02 | Phase 3 | Dashboard | Build real-time before/after sensor dashboard | Nash | Critical | Done | Sep 20 | Show 5 pre/post parameters, total volume, device status and last update using simulator first. | P1-05 or P2-02
P3-03 | Phase 3 | Dashboard | Build live water-route/status visualization | Nash | High | Done | Sep 21 | Visualize Source → Pump → Pre Sensors → UF → UV-C → Post Sensors → Output with on/off/error states. | P3-02
P3-04 | Phase 3 | History | Build historical charts and data table | Nash | High | Done | Sep 23 | Create pre/post charts, units, date filters and raw table. | P2-03
P3-05 | Phase 3 | Alerts UI | Build alerts and diagnostics page | Nash | High | Done | Sep 25 | Show alert type, severity, timestamp, status and diagnostics. | P2-05
P3-06 | Phase 3 | Offline UX | Implement stale/offline dashboard state | Nash | High | Done | Sep 24 | Freeze last values and show clear offline/stale warning plus timestamp. | P2-03
P4-01 | Phase 4 | Test Runs | Build experiment/test-run workflow | Nash | High | Done | Sep 26 | Create/start/end test run, sample ID and notes; link telemetry. | P2-01
P4-02 | Phase 4 | Calibration | Build calibration record page | Nash | Medium | Done | Sep 27 | Save calibration date, sensor, raw/reference values, factor/offset and notes. | Sensor calibration procedure
P4-03 | Phase 4 | Lab Validation | Build laboratory validation records | Nash | High | Done | Sep 28 | Record before/after lab results, sample ID, date and reference number. | P2-01
P4-04 | Phase 4 | Research Analysis | Build sensor-vs-lab comparison and percentage error | Nash | High | Done | Sep 30 | Create comparison table and safe percentage-error calculation. | P4-03
P3-07 | Phase 3 | UI/UX | Complete and approve 8-screen UI/UX design package | Nash | High | Done | Sep 15 | Approved Dashboard, History, Alerts, Test Runs, Calibration, Laboratory Validation, Maintenance and Settings; clean references stored under docs/ui/approved. | Client requirements / approved Stitch references
P3-08 | Phase 3 | Frontend Integration | Prepare frontend service layer for backend integration | Nash | Critical | Done | Sep 15 | Centralized typed API client via VITE_API_BASE_URL; domain services, mock adapters, resource states and mutation boundaries prepared without inventing unapproved backend routes. Included in frontend commit 0a28ed012707b57c9dc10d5ce908bf8b0621aa54 on feature/frontend-foundation. Working tree clean; no uncommitted files. Push/merge not yet performed. | P3-01, docs/API_CONTRACT.md
P4-05 | Phase 4 | Maintenance / Settings | Build Maintenance and Settings frontend modules | Nash | Medium | Done | Sep 15 | Implemented maintenance records/reminders plus software configuration/access-management UI; no unconfirmed hardware-control behavior was added. | Approved UI references
P5-01 | Phase 5 | Firmware | Create PlatformIO ESP32-WROOM-32 firmware project | Edgar | Critical | Not Started | Sep 17 | Create modular firmware structure, config handling, Wi-Fi state and serial logging. | P1-01
P5-02 | Phase 5 | Sensor Drivers | Integrate PH-4502C pair | Edgar | High | Not Started | Sep 21 | Test each pH channel, raw ADC and calibrated values; document pins. | Final pin map
P5-03 | Phase 5 | Sensor Drivers | Integrate DFRobot TDS pair | Edgar | High | Not Started | Sep 22 | Implement two channels, calibration and raw/converted logging. | Final pin map
P5-04 | Phase 5 | Sensor Drivers | Integrate DS18B20 pair | Edgar | High | Not Started | Sep 21 | Identify both OneWire addresses and implement error handling. | Final pin map
P5-05 | Phase 5 | Sensor Drivers | Integrate ZJ-S201C flow pair | Edgar | High | Not Started | Sep 23 | Use pulse counting/interrupts; calculate flow rate and total volume; calibrate. | Flow calibration reference
P5-06 | Phase 5 | Sensor Drivers | Integrate turbidity pair | Edgar | High | Waiting Client | Sep 24 | Wait for exact model, then implement voltage/ADC conversion and calibration. | P0-03
P5-07 | Phase 5 | Device Logic | Implement sensor-fault detection | Edgar | Critical | Not Started | Sep 25 | Detect invalid/disconnected sensors locally and expose fault flags. | All sensor drivers
P5-08 | Phase 5 | Device Logic | Implement offline-safe operation and cycle timer | Edgar | Critical | Not Started | Sep 27 | Build local state machine that works without internet and supports 1-hour maximum. | P0-05, P0-07
P5-09 | Phase 5 | Connectivity | Send real telemetry/status to backend over HTTPS | Edgar | Critical | Not Started | Sep 29 | Implement Wi-Fi reconnect, JSON payload and retry/backoff. | P2-02, P5-01
P6-01 | Phase 6 | Integration | Replace simulator with real ESP32 telemetry | Alejandro | Critical | Not Started | Oct 1 | Validate mapping, timestamps, units and online status from real device. | P5-09, P3-02
P6-02 | Phase 6 | Control Integration | Integrate pump/UV-C/relay status or control | Edgar | Critical | Waiting Client | Oct 2 | Implement only after control authority and component specs are confirmed. | P0-04, P0-05
P6-03 | Phase 6 | Alerts Integration | Connect firmware faults to backend/dashboard alerts | Alejandro | High | Not Started | Oct 3 | Map fault codes and quality alerts to clear diagnostics. | P5-07, P2-05
P6-04 | Phase 6 | Full System Test | Run end-to-end filtration session with live data | Nash | Critical | Not Started | Oct 3 | Run one full cycle, save test-run data and verify export. | Working assembled prototype
P7-01 | Phase 7 | Calibration | Calibrate sensors and record calibration data | Edgar | Critical | Not Started | Oct 4 | Perform reference calibration for all sensors and store factors/results. | Reference solutions/instruments
P7-02 | Phase 7 | Accuracy | Run sensor vs reference/lab accuracy tests | Edgar | High | Not Started | Oct 5 | Collect paired sensor/reference values and export percentage-error results. | P7-01, lab/reference values
P7-03 | Phase 7 | Reliability | Test Wi-Fi loss, ESP32 reboot, stale dashboard and sensor failure | Nash | Critical | Not Started | Oct 6 | Run fault scenarios and confirm expected local fail-safe/offline behavior. | P6-03
P7-04 | Phase 7 | QA | Verify exports and final dashboard usability | Nash | High | Not Started | Oct 7 | Check CSV, charts, login, responsiveness, units and missing-data handling. | Core features complete
P8-01 | Phase 8 | Deployment | Deploy frontend, backend and production database config | Nash | Critical | Not Started | Oct 7 | Deploy Vercel/Render/Supabase, configure secrets and test public URL. | P6 complete
P8-02 | Phase 8 | Documentation | Finalize README, architecture, API and operator guide | Nash | High | Not Started | Oct 8 | Document startup, shutdown, common errors, integration and recovery. | All core features
P8-03 | Phase 8 | Defense Prep | Create final demo checklist and backup plan | Nash | Critical | Not Started | Oct 8 | Freeze features; prepare local fallback, sample data and exact demo sequence. | P8-01
P8-04 | Phase 8 | Defense Prep | Full rehearsal with hardware team | Nash | Critical | Not Started | Oct 9 | Rehearse power-on → dashboard → test run → alerts → export. | All hardware/software ready
P8-05 | Phase 8 | Defense | Final defense support | Nash | Critical | Not Started | Oct 10 | Support stable final demo with backups, chargers and local build. | P8-04

## Client Requirements
Category | Requirement / Question | Client Answer | Status | Software / Project Impact | Follow-up Owner | Target | Source / Link
Project Status | Current prototype status | Components purchased; assembly in progress; some parts tested. Sensor scripts are individual only and not integrated. | Confirmed | Software can start in parallel using simulator; hardware integration comes later. | Nash | Sep 14 | Client Phase 0 Form, 2026-09-11
Microcontroller | Board/model | ESP32 WROOM 32 | Confirmed | Use PlatformIO + Arduino framework targeting ESP32-WROOM-32. | Edgar | Sep 14 | https://documentation.espressif.com/esp32-wroom-32_datasheet_en.pdf
pH | Sensor | PowerMav Electronics PH-4502C, Qty 2 | Confirmed | Pre and post pH channels required. | Edgar | Sep 21 | https://powermavelectronics.com/shop/module/ph-sensor-module-set/
Turbidity | Sensor | Qty 2; exact brand/model not provided | Pending | Cannot finalize ADC conversion/calibration until model is known. | Edgar | Sep 15 | Client Phase 0 Form, 2026-09-11
TDS | Sensor | DFRobot TDS sensor, Qty 2 | Confirmed | Pre and post TDS channels required. | Edgar | Sep 22 | https://mm.digikey.com/Volume0/opasdata/d220001/medias/docus/2309/SEN0244_Web.pdf
Temperature | Sensor | PowerMav DS18B20, Qty 2 | Confirmed | Use two uniquely addressed probes. | Edgar | Sep 21 | https://www.analog.com/media/en/technical-documentation/data-sheets/ds18b20.pdf
Flow | Sensor | PowerMav ZJ-S201C, Qty 2 | Confirmed | Need pre/post flow rate and total volume calculation. | Edgar | Sep 23 | https://powermavelectronics.com/shop/sensor/water-flow-sensor-zj-s201c/
Sensor Placement | Before/after layout | One sensor set before filtration and one set after filtration. | Confirmed | Dashboard/database must be designed for direct before-vs-after comparison. | Nash | Sep 14 | Client Phase 0 Form, 2026-09-11
Water Flow | Final sequence | Water Source → Booster Pump → Sensors → Ultrafiltration → UVC → Sensors → LCD → Output | Confirmed | Use sequence in live water-route UI and integration tests. | Nash | Sep 14 | Client Phase 0 Form, 2026-09-11
Automation | Automatically controlled components | Client selected “Automatic sensor control”; pump/UV-C control not clearly selected. | Clarify | Control architecture cannot be finalized until actuator authority is confirmed. | Nash | Sep 15 | Client Phase 0 Form, 2026-09-11
Actuator | Relay | 4-channel relay module | Partial | Need exact board/model and voltage logic. | Edgar | Sep 15 | Client Phase 0 Form, 2026-09-11
Actuator | Pump | Model/voltage not provided | Pending | Needed for control/status logic and electrical safety boundaries. | Edgar | Sep 15 | Client Phase 0 Form, 2026-09-11
Actuator | UV-C | Exact module/specifications not provided | Pending | Needed for status/control and UV-C runtime tracking. | Edgar | Sep 15 | Client Phase 0 Form, 2026-09-11
Control Rule | Maximum cycle | Maximum operational limit of 1 hour per filtration cycle. | Confirmed | ESP32 state machine must enforce local maximum timer. | Edgar | Sep 27 | Client Phase 0 Form, 2026-09-11
Control Rule | Sensor failure | Stop water flow if any sensor fails or disconnects. | Confirmed | Critical fail-safe must happen locally on ESP32, not depend on website. | Edgar | Sep 25 | Client Phase 0 Form, 2026-09-11
Offline | Internet loss | Dashboard freezes/displays last recorded data; hardware continues basic operation offline. | Confirmed | Implement stale-data UI + local ESP32 operation. | Nash | Sep 24 | Client Phase 0 Form, 2026-09-11
Website | Realtime data | pH, turbidity, TDS, temperature, flow, total volume, pump, UV-C, filtration, ESP32 online/offline, last update. | Confirmed | These fields define the MVP dashboard contract. | Nash | Sep 20 | Client Phase 0 Form, 2026-09-11
Website | Live water route | Stable / on / off route visualization requested. | Confirmed | Add route/status visualization based on device states. | Nash | Sep 21 | Client Phase 0 Form, 2026-09-11
Website | Core features | Realtime dashboard, current readings, status, history, charts, alerts, table, CSV export. | Confirmed | All included in planned scope. | Nash | Sep 25 | Client Phase 0 Form, 2026-09-11
Research | Research/testing features | Test runs, before/after records, calibration, lab validation, sensor-vs-lab, % error, power records. | Confirmed | Create dedicated research modules/tables. | Alejandro | Sep 30 | Client Phase 0 Form, 2026-09-11
Optional | Accounts/features | Login, admin, roles, remote manual control, maintenance, filter reminder, UV-C hours. | Confirmed | Include after core MVP; remote control depends on actuator clarification. | Nash | Oct 1 | Client Phase 0 Form, 2026-09-11
Notification | SMS fault/error alerts | Requested | Confirmed | Create provider-neutral alert service; choose SMS provider later. | Alejandro | Sep 27 | Client Phase 0 Form, 2026-09-11
Alerts | Required alert types | ESP32 offline, sensor error, no flow, abnormal pH, high turbidity/TDS, temp warning, pump/UV-C problems, filter clogged. | Confirmed | Backend + device fault model must support these categories. | Alejandro | Oct 3 | Client Phase 0 Form, 2026-09-11
Thresholds | Approved numeric thresholds | All fields left blank | Pending | Quality alerts must remain non-final until adviser-approved values are provided. | Nash | Sep 18 | Client Phase 0 Form, 2026-09-11
Deployment | Internet during defense | Reliable Wi-Fi: Yes | Confirmed | Can use public cloud, but local fallback is still required. | Nash | Sep 14 | Client Phase 0 Form, 2026-09-11
Deployment | Website access | Both local network and public internet | Confirmed | Plan public deployment + local fallback/backup. | Nash | Oct 7 | Client Phase 0 Form, 2026-09-11
Data Timing | Save/monitor interval | Every 30 seconds selected; also “to be determined during testing” and one cycle per 1 liter processed. | Clarify | Separate sensor sampling, DB persistence and cycle completion rules. | Nash | Sep 16 | Client Phase 0 Form, 2026-09-11
Schedule | Final defense date | October 10, 2026 | Confirmed | Feature freeze planned for October 8. | Nash | Sep 14 | Client Phase 0 Form, 2026-09-11

## Risks & Issues
ID | Risk / Issue | Impact | Likelihood | Severity | Owner | Mitigation / Next Action | Evidence | Status | Due
R-01 | Exact turbidity sensor model is missing | Firmware/calibration for 2 channels cannot be finalized | High | High | Edgar | Get exact model/link/datasheet before implementing conversion logic. | Client left model blank. | Open | Sep 15
R-02 | Pump/UV-C electrical specs are missing | Unsafe or incompatible control integration risk | High | Critical | Edgar | Do not control until model, voltage/current and relay interface are confirmed. | Pump and UV-C fields blank. | Open | Sep 15
R-03 | Reference wiring/pin diagram is AI-generated | Potential wrong pins or unsafe assumptions | High | Critical | Edgar | Create a verified pin map from actual hardware. | Client marked diagram as reference only. | Open | Sep 17
R-04 | Pump/UV-C control scope is ambiguous | Remote control and fail-safe design may conflict | High | High | Nash | Get explicit monitor-only vs controllable decision. | Remote control selected but auto-control boxes not selected. | Open | Sep 15
R-05 | Alert thresholds are not approved | Cannot safely label abnormal water-quality values | High | High | Nash | Request adviser-approved values; keep threshold alerts pending. | Threshold section blank. | Open | Sep 18
R-06 | Short timeline before Oct 10 defense | Feature overload may threaten stability | High | Critical | Nash | Prioritize MVP and freeze features Oct 8. | Many optional features selected. | Open | Oct 8
R-07 | Internet/cloud dependency during demo | Cloud outage could break dashboard | Medium | High | Alejandro | Frontend stale/offline state is implemented. Complete backend connectivity handling and local ESP32 autonomy/fallback. | Frontend v1 includes stale/offline resource states; hardware-side autonomy still pending. | In Progress | Oct 7
R-08 | SMS provider not chosen | SMS feature could delay core work | Medium | Medium | Alejandro | Build provider-neutral notification service first. | SMS requested without provider. | Open | Sep 27
R-09 | Sensor failure must stop water flow | Critical safety logic depends on actuator control path | High | Critical | Edgar | Confirm hardware mechanism; implement local fail-safe only after control design approval. | Client requirement. | Open | Sep 25
R-10 | Website may imply water is safe to drink from sensors alone | Scientific/defense risk | Medium | High | Nash | Keep neutral sensor wording and separate Laboratory Validation from sensor telemetry throughout backend integration and defense demo. | Frontend v1 avoids automatic potability claims and keeps Laboratory Validation as a separate research record. | Mitigated / Monitor | Sep 20

## Team Roles
Member | Primary Role | Owns | Supports | Key Outputs | Working Rule
Nash | Project Lead / Frontend | Requirements, tracker, architecture, frontend, integration, deployment, client communication | Backend, ESP32 troubleshooting, QA | Dashboard, frontend modules, project decisions, deployment, defense plan | Can work across all roles; final integrator and scope decision-maker.
Alejandro | Backend Developer | Node/Express API, Supabase DB, auth, realtime, alerts logic, CSV export | Frontend integration, deployment, simulator | Database schema, API endpoints, backend services, production config | Coordinate API contract with Nash and telemetry payload with Edgar.
Edgar | ESP32 / Hardware Integration | ESP32 firmware, sensor drivers, local state machine, hardware/software integration, fault detection | Backend payload integration, hardware team coordination | Reliable sensor readings, device telemetry, fail-safe logic, verified pin map | Do not wire/control unverified components; document all final pins/specs.
TEAM WORKFLOW | Nash maintains priorities and client communication. Alejandro and Edgar update task status before team check-ins. API/schema changes require team agreement. Hardware assumptions must be verified before final firmware. After Oct 8, only bug fixes and defense prep.